## BSPT Actions
Baseline Symbology Project Team (BSPT) Workplan 2022
Ref # | Task | Details | Who | Start date | End Date | Status | Remarks
1 | Establish Virtual Working Environment for Project Team
1.1 | Create a space to store working documents |  | DB and JW | 2022-01-19 |  | In progress
1.2 | Provide means to comment on documents and interact with other team members |  | DB and JW | 2022-01-19 |  | In progress
2 | Create Digital Paper Chart Symbol Library
2.1 | Develop list of S-4 Symbols
2.2 | Identify existing digital symbol sets |  | DB | 2022-01-19 |  | In-Progress
2.3 | Determine a single set of S-4 symbols for use in automated paper chart generation from all symbol sets available
2.4 | Convert digital symbols that are available in other formats to SVG
2.5 | Create new SVGs for symbols that have no digital equivalent
2.6 | Apply for and establish a "Paper Chart" Domain within the IHO GI Registry Portrayal Register to store SVGs |  | DB, NCWG Chair, GI Registry Manager
3 | Collect and Create Paper Chart Portrayal Rules (portrayal comprises both symbolization and associated text labeling)
3.1 | Identify existing digital portrayal rules
3.2 | Develop standard format for paper chart portrayal rules to be captured, stored, and used
3.3 | Create new paper chart portrayal rules when none exists
3.4 | Assess the usefulness of the S-101 ENC Product Specification for to support the automation of paper chart production
4 | Testing
4.1 | Assemble a suitable collection of ENC data for automation testing. | Data should represent a variety of feature/attribute types and compilation/data density/labeling situations
4.2 | Assemble a collection of corresponding “standard” paper nautical charts to compare with ENC data to paper chart automation output
4.3 | Test ENC data to Paper Chart Automation
5
5.1
6
6.1