## BSPT Actions
Baseline Symbology Project Team (BSPT) Workplan 2022
Ref # | Task | Details | Who | Start date | End Date | Status | Remarks
1 | Establish Virtual Working Environment for Project Team
1.1 | Create a space to store working documents |  | DB and JW | 2022-01-19 |  | In progress
1.2 | Provide means to comment on documents and interact with other team members |  | DB and JW | 2022-01-19 |  | In progress
2 | Create Digital Paper Chart Symbol Library
2.1 | Develop list of S-4 Symbols
2.2 | Identify existing digital symbol sets |  | DB | 2022-01-19 |  | In-Progress
2.3 | Convert digital symbols that are available in other formats to SVG
2.4 | Create new SVGs for symbols that have no digital equivalent
2.5 | Implement “Automated Chart Symbology” S-100 Portrayal Register to store SVGs
3 | Collect and Create Paper Chart Portrayal Rules (portrayal comprises both symbolization and associated text labeling)
3.1 | Identify existing digital portrayal rules
3.2 | Develop standard format for portrayal rules to be captured, stored, and used
3.3 | Create new portrayal rules when none exists
3.4 | Assess the usefulness of S-101 ENC Specification for the automation of paper chart production
4 | Testing
4.1 | Assemble a suitable collection of ENC data for automation testing. Data should represent a variety of feature/attribute types and compilation/data density/labeling situations
4.2 | Assemble a collection of corresponding “standard” paper nautical charts to compare ENC paper chart automation output to
4.3 | Test ENC to Paper Chart Automation
5
5.1
6
6.1

## Completed_Closed
Source | Action | Detail | Lead | Status | Remarks
S-101PT4-01 | Finish the S-57 to S-101 Conversion Report
S-101PT4-02 | S-101 ENC Portrayal
S-101PT4-03 | Update S-101 to final IHO GI Registry
S-101PT4-04 | Validation Checks
S-101PT4-05 | S-57 to S-101 Convertor
S-101PT4-08 | S-57 to S-101 Portrayal Gap Analysis
S-101PT4-09 | Offshore Solar Farms
S-101PT4-10 | DCEG Changes for S-101 Edition 2.0.0
S-101PT4-11 | DCEG Changes for S-101 Edition 2.0.0
S-101PT4-12 | Proposal of Alternate Options for Display Scale
S-101PT4-13 | Quality of Horizontal Measurement
S-100TSM7 | Visualization of Quality of Bathymetric Data
S-100TSM7 | Alerts and Indications
S-100TSM7 | Alerts and Indications
S-100TSM7 | Alerts and Indications
S-101PT5-01 | Quality of Horizontal Measurement
S-101PT5-02 | Visualization of Quality of Bathymetric Data
S-101PT5-04 | Changes Intoduced in S-101 Edition 1.1.0 DCEG
S-101PT5-05 | Changes Intoduced in S-101 Edition 1.1.0 DCEG
S-101PT5-06 | Changes Intoduced in S-101 Edition 1.1.0 DCEG
S-101PT5-08 | Portrayal
S-101PT5-10 | Validation Checks
S-101PT5-11 | S-101PT Work Plan
S-101PT5-12 | S-101PT Work Plan
S-101PT5-14 | Navigational Purposes
S-101PT5-12 | S-101PT Work Plan
S-101PT5-15 | VALSOU Decimal Places
S-101PT5-16 | VALSOU Decimal Places
S-101PT5-17 | Fairway Portrayal
S-101PT5-18 | Light Sector Portrayal
S-101PT5-19 | Quality of Bathymetric data and ECDIS Performance
S-101PT5-20 | Grouping of Soundings
S-101PT5-22 | S-57 to S-101 Encoding
S-101PT5-24 | NIWC Testbed Update
S-101PT5-25 | NIWC Testbed Update
S-101PT5-26 | NIWC Testbed Update
S-101PT6-04 | S-101PT6-06 - DCEG Update
S-101PT5-24 | NIWC Testbed Update
S-101PT5-25 | NIWC Testbed Update
S-101PT5-26 | NIWC Testbed Update
S-101PT6-02 | DCEG Update
S-101PT6-03 | DCEG Update
S-101PT6-04 | DCEG Update
S-101PT6-07 | Portrayal Progress
S-101PT6-09 | Validation Update
S-101PT6-13 | S-101 Roadmap
S-101PT6-14 | S-101 Issues Log
S-101PT6-15 | Bathymetric Data Quality
S-101PT6-16 | Portrayal of Small Craft Mooring Areas
S-101PT6-17 | Quality of Horizontal Measurement
S-101PT6-19 | Placement of Texts in S-101